## Roadmap
Workday VMS Expansion Roadmap - Module Tracker
Summary | Value
Total modules | 24
Total checklist items | 245
Overall completion | 8.163%
ID | Module | Phase | Priority | Dependencies | Effort | Primary outcome | Completion | Module Done | Notes
M00 | Freeze Hackathon Baseline & Repository Governance | Phase A - Preserve & harden | P0 | None | S | Preserve the two-day hackathon result as a verifiable baseline, then make every post-hackathon change traceable and deliberate. | 100% | ☑ | Completed 2026-09-06: owner-created v1.0-hackathon points to 4bd5cd1.
M01 | Automated Regression Suite & CI | Phase A - Preserve & harden | P0 | M00 | M | Turn the current ad-hoc live-server scripts into a repeatable safety net before changing business workflows. | 100% | ☑ | Completed 2026-09-06: automated regression, coverage, frontend tests, and CI added.
M02 | Authentication, Session & Account Security Hardening | Phase A - Preserve & harden | P0 | M01 | M | Replace hackathon-grade authentication with a production-shaped session and account-recovery design. | 0% | ☐
M03 | Structured Logging, Error Contracts & Operational Health | Phase A - Preserve & harden | P0 | M01 | S-M | Make failures diagnosable without exposing internals to users. | 0% | ☐
M04 | Transactional Audit Logging Foundation | Phase A - Preserve & harden | P0 | M01,M03 | M | Create a real who-did-what-when trail for business-critical state changes. | 0% | ☐
M05 | API Scalability, Search/Filtering & API Documentation | Phase A - Preserve & harden | P0 | M01,M03 | M | Make list endpoints scale beyond demo data and make the API contract explicit. | 0% | ☐
M06 | Timesheet Workflow Completion | Phase B - Workforce operations | P1 | M01,M04,M05 | L | Complete the contractor -> submit -> PM review -> reject with reason -> correct -> resubmit workflow while preserving daily-row accuracy. | 0% | ☐
M07 | Contractor Profile & Multi-Skill Model | Phase B - Workforce operations | P1 | M01,M05 | L | Move from one hard-coded skill enum to a credible contractor profile used by staffing decisions. | 0% | ☐
M08 | Contractor Document Verification & Compliance Gate | Phase B - Workforce operations | P1 | M04,M07 | L | Implement document upload/review and prevent unverified contractors from being staffed. | 0% | ☐
M09 | Client Management, Vendor-Client Relationships & Project Visibility | Phase B - Workforce operations | P1 | M02,M04,M05 | L | Turn client companies into an explicit business relationship and stop every vendor from seeing/staffing every project. | 0% | ☐
M10 | Project, Requirement, Budget & Time-Policy Lifecycle | Phase B - Workforce operations | P1 | M04,M09 | L | Allow projects and staffing requirements to evolve safely after creation and add the missing commercial/time-policy fields. | 0% | ☐
M11 | Contractor Availability & Date-Based Assignment Lifecycle | Phase B - Workforce operations | P1 | M07,M08,M10 | L | Replace the global one-ACTIVE-assignment rule with date-aware availability and controlled individual release. | 0% | ☐
M12 | Candidate Submission -> PM Acceptance Workflow | Phase B - Workforce operations | P1 | M09,M11 | L | Replace direct vendor assignment with a realistic propose-review-accept staffing flow. | 0% | ☐
M13 | Staffing Pipeline, Approval SLA & Escalation | Phase B - Workforce operations | P1 | M12,M10 | M | Turn candidate records into operational staffing visibility and highlight items waiting too long. | 0% | ☐
M14 | In-App Notifications & Preferences | Phase B - Workforce operations | P1 | M06,M12,M13 | M | Notify the right role when another role creates work that needs attention. | 0% | ☐
M15 | Rate Cards, Assignment Rate Snapshots & Rate History | Phase C - Commercial lifecycle | P1 | M09,M11 | L | Separate commercial client bill rates from contractor cost/default rates and make rate changes historically safe. | 0% | ☐
M16 | Milestone Management Enhancement | Phase C - Commercial lifecycle | P1 | M06,M10,M15 | M | Keep the proven project-wide hours trigger while making milestones understandable and operationally manageable. | 0% | ☐
M17 | Invoice Lifecycle Redesign: Billing Queue -> Vendor Draft -> Client Approval | Phase C - Commercial lifecycle | P1 | M09,M15,M16,M01 | XL | Correct the commercial ownership model: milestones create billing eligibility; Vendor creates/submits an invoice; Client/PM approves or rejects it. | 0% | ☐
M18 | Invoice Numbers, Line Items, Tax & PDF Document | Phase C - Commercial lifecycle | P1 | M17 | L | Make an approved/submitted invoice a real business document rather than a JSON row. | 0% | ☐
M19 | Payment & Outstanding Tracking | Phase C - Commercial lifecycle | P1 | M17,M18 | M | Separate client approval from actual payment and expose outstanding/overdue money. | 0% | ☐
M20 | Business Dashboards, Financial Health & CSV Exports | Phase C - Commercial lifecycle | P2 | M05,M10,M13,M15,M19 | L | Make dashboards reflect the full workforce/commercial lifecycle with precise terminology and exportable operational data. | 0% | ☐
M21 | Contractor Offboarding, History & Project Close Safeguards | Phase D - Portfolio-grade operations | P2 | M11,M19,M04 | M | Close assignments/projects cleanly without losing historical workforce or billing records. | 0% | ☐
M22 | Production Deployment, Backup, Security & Demo Environment | Phase D - Portfolio-grade operations | P2 | M01,M02,M03,M20 | L | Make the expanded system reproducible and demonstrable outside the development machine. | 0% | ☐
M23 | Final Architecture Audit, Release & Internship Story | Phase D - Portfolio-grade operations | P2 | M00-M22 | M | Validate that the expanded platform is coherent, tested and explainable, then cut a portfolio release. | 0% | ☐

## Checklist
Detailed Implementation & Acceptance Checklist
Tracker | Value
Completed | 20 | Remaining | 225
Completion | 8.163%
Module ID | Module | Phase | Priority | Type | Area | Task | Dependencies | Owner | Done | Notes | Completed Date
M00 | Freeze Hackathon Baseline & Repository Governance | Phase A - Preserve & harden | P0 | Implementation | Repository | Create Git tag/release `v1.0-hackathon` at the exact hackathon-complete commit; do not mix later refactors into that baseline. | None |  | ☑ | Baseline tag v1.0-hackathon verified at 4bd5cd1. | 2026-09-06
M00 | Freeze Hackathon Baseline & Repository Governance | Phase A - Preserve & harden | P0 | Implementation | Documentation | Rewrite root README as current-system documentation: roles, architecture, setup, implemented end-to-end workflow, demo accounts/data, and module map. | None |  | ☑ | Current-system README completed. | 2026-09-06
M00 | Freeze Hackathon Baseline & Repository Governance | Phase A - Preserve & harden | P0 | Implementation | Documentation | Add `ARCHITECTURE.md`, `DATABASE.md`, `API.md`, `CHANGELOG.md`, `ROADMAP.md`, and a short ADR folder for major decisions. | None |  | ☑ | Architecture, database, API, roadmap, changelog, and ADRs added. | 2026-09-06
M00 | Freeze Hackathon Baseline & Repository Governance | Phase A - Preserve & harden | P0 | Implementation | Governance | Document invariants to preserve: JWT-derived identity, role-scoped routes, ownership checks in SQL, identical 404 for cross-tenant probes, explicit transactions/row locks, DB uniqueness as concurrency backstop, immutable billing snapshots, post-commit side effects. | None |  | ☑ | Security, tenancy, locking, uniqueness, and financial invariants documented. | 2026-09-06
M00 | Freeze Hackathon Baseline & Repository Governance | Phase A - Preserve & harden | P0 | Implementation | Cleanup | Mark or remove obsolete verification-only routes/files only after equivalent real tests exist; retain historical notes where they explain superseded behavior. | None |  | ☑ | Historical e2e retained; verification-only routes deferred to M01 pending real tests. | 2026-09-06
M00 | Freeze Hackathon Baseline & Repository Governance | Phase A - Preserve & harden | P0 | Implementation | Workflow | Adopt the permanent cycle: implement -> manual E2E -> short architecture/security audit -> automated tests -> commit/push -> next module. | None |  | ☑ | Permanent lifecycle recorded in ROADMAP.md and Expansion Doc. | 2026-09-06
M00 | Freeze Hackathon Baseline & Repository Governance | Phase A - Preserve & harden | P0 | Acceptance | Acceptance Criteria | Hackathon baseline is tagged and reproducible. | None |  | ☑ | Annotated baseline tag verified locally at 4bd5cd1. | 2026-09-06
M00 | Freeze Hackathon Baseline & Repository Governance | Phase A - Preserve & harden | P0 | Acceptance | Acceptance Criteria | A new developer can understand the current system from README/architecture docs without reading every source file. | None |  | ☑ | README and architecture documentation independently verified. | 2026-09-06
M00 | Freeze Hackathon Baseline & Repository Governance | Phase A - Preserve & harden | P0 | Acceptance | Acceptance Criteria | Every future module has an explicit changelog entry and commit boundary. | None |  | ☑ | Changelog entry and owner-controlled commit boundary established. | 2026-09-06
M01 | Automated Regression Suite & CI | Phase A - Preserve & harden | P0 | Implementation | Backend | Add Jest + Supertest (or equivalent) and an isolated `vms_test` database configuration that refuses to run against a non-test DB. | M00 |  | ☑ | Node test runner and guarded vms_test configuration added. | 2026-09-06
M01 | Automated Regression Suite & CI | Phase A - Preserve & harden | P0 | Implementation | Database | Run migrations automatically for tests; provide deterministic seed/factory helpers instead of relying on a manually prepared live database. | M00 |  | ☑ | Each backend run recreates vms_test and applies migrations 001-016. | 2026-09-06
M01 | Automated Regression Suite & CI | Phase A - Preserve & harden | P0 | Implementation | Regression | Port existing scenarios: RBAC/ownership, atomic assignment, no overstaffing, active-assignment conflict/release, PM allocation caps, daily timesheet uniqueness, rejected edit/resubmit, milestone trigger, per-contractor billing contribution, duplicate invoice protection. | M00 |  | ☑ | Current MVP and release regression scenarios are automated. | 2026-09-06
M01 | Automated Regression Suite & CI | Phase A - Preserve & harden | P0 | Implementation | Concurrency | Add tests that run simultaneous assignment/review/invoice operations and assert only one valid winner where uniqueness/conditional transitions apply. | M00 |  | ☑ | Concurrent approval/billing duplicate protection is exercised. | 2026-09-06
M01 | Automated Regression Suite & CI | Phase A - Preserve & harden | P0 | Implementation | Frontend | Add Vitest/React Testing Library for role routing, critical forms, rejection reason visibility, assignment state, timesheet state, and invoice state as modules evolve. | M00 |  | ☑ | Vitest route-guard coverage added; further UI states evolve with modules. | 2026-09-06
M01 | Automated Regression Suite & CI | Phase A - Preserve & harden | P0 | Implementation | CI | Add GitHub Actions: install -> lint -> backend tests -> MySQL integration tests -> frontend tests -> production build. | M00 |  | ☑ | GitHub Actions runs MySQL-backed tests, lint, frontend tests, and build. | 2026-09-06
M01 | Automated Regression Suite & CI | Phase A - Preserve & harden | P0 | Implementation | Quality | Set a practical coverage floor for core services/repositories rather than chasing 100%; make failing tests block merges. | M00 |  | ☑ | c8 gate: 40% lines/functions, 30% branches for services/repositories. | 2026-09-06
M01 | Automated Regression Suite & CI | Phase A - Preserve & harden | P0 | Acceptance | Acceptance Criteria | `npm test` runs without manually starting the API. | M00 |  | ☑ | npm test starts its own local API and test database workflow. | 2026-09-06
M01 | Automated Regression Suite & CI | Phase A - Preserve & harden | P0 | Acceptance | Acceptance Criteria | CI creates an isolated MySQL service and passes from a clean checkout. | M00 |  | ☑ | CI provisions isolated MySQL 8 service. | 2026-09-06
M01 | Automated Regression Suite & CI | Phase A - Preserve & harden | P0 | Acceptance | Acceptance Criteria | The known milestone billing regression is permanently covered. | M00 |  | ☑ | Known milestone billing regression passes in automated suite. | 2026-09-06
M01 | Automated Regression Suite & CI | Phase A - Preserve & harden | P0 | Acceptance | Acceptance Criteria | A concurrency race cannot silently pass as two successful mutations. | M00 |  | ☑ | Concurrent milestone approvals assert no duplicate billing contributions. | 2026-09-06
M02 | Authentication, Session & Account Security Hardening | Phase A - Preserve & harden | P0 | Implementation | Security | Add `helmet`, strict CORS allowlist by environment, request body limits, auth-specific rate limiting and progressive account lockout/backoff. | M01 |  | ☐
M02 | Authentication, Session & Account Security Hardening | Phase A - Preserve & harden | P0 | Implementation | Sessions | Move to short-lived access tokens plus refresh/session records with rotation, revocation and logout-all; prefer an HttpOnly Secure SameSite refresh cookie rather than a long-lived localStorage bearer token. | M01 |  | ☐
M02 | Authentication, Session & Account Security Hardening | Phase A - Preserve & harden | P0 | Implementation | Recovery | Implement forgot-password/reset-password using single-use hashed reset tokens with expiry; enforce the same password policy as signup. | M01 |  | ☐
M02 | Authentication, Session & Account Security Hardening | Phase A - Preserve & harden | P0 | Implementation | Contractor onboarding | Replace vendor-chosen permanent passwords with invitation/first-login password setup. Keep a temporary compatibility path only while migrating seed/demo users. | M01 |  | ☐
M02 | Authentication, Session & Account Security Hardening | Phase A - Preserve & harden | P0 | Implementation | Validation | Reject unknown auth fields; normalize email consistently; keep generic login/recovery responses that do not reveal account existence. | M01 |  | ☐
M02 | Authentication, Session & Account Security Hardening | Phase A - Preserve & harden | P0 | Implementation | Frontend | Add session restoration, expired-session handling, password setup/reset screens, logout-all entry point, and clear unauthorized vs expired states. | M01 |  | ☐
M02 | Authentication, Session & Account Security Hardening | Phase A - Preserve & harden | P0 | Implementation | Tests | Cover brute-force limits, token rotation/reuse rejection, logout revocation, reset-token expiry/reuse, and contractor invitation acceptance. | M01 |  | ☐
M02 | Authentication, Session & Account Security Hardening | Phase A - Preserve & harden | P0 | Acceptance | Acceptance Criteria | Repeated failed logins are rate-limited/locked safely. | M01 |  | ☐
M02 | Authentication, Session & Account Security Hardening | Phase A - Preserve & harden | P0 | Acceptance | Acceptance Criteria | A stolen/expired access token can be revoked via the session model. | M01 |  | ☐
M02 | Authentication, Session & Account Security Hardening | Phase A - Preserve & harden | P0 | Acceptance | Acceptance Criteria | Forgot-password works without leaking whether an email exists. | M01 |  | ☐
M02 | Authentication, Session & Account Security Hardening | Phase A - Preserve & harden | P0 | Acceptance | Acceptance Criteria | Vendor-created contractors set their own password on first login. | M01 |  | ☐
M03 | Structured Logging, Error Contracts & Operational Health | Phase A - Preserve & harden | P0 | Implementation | Logging | Introduce structured JSON logs with request_id/correlation_id, route, actor user id/role, status, duration and stable error code; redact passwords/tokens/document data. | M01 |  | ☐
M03 | Structured Logging, Error Contracts & Operational Health | Phase A - Preserve & harden | P0 | Implementation | Middleware | Generate/accept a request ID at ingress and return it in response headers/errors. | M01 |  | ☐
M03 | Structured Logging, Error Contracts & Operational Health | Phase A - Preserve & harden | P0 | Implementation | Errors | Standardize API errors as `{code,message,details?,request_id}`; map DB duplicate/constraint failures to stable domain codes. | M01 |  | ☐
M03 | Structured Logging, Error Contracts & Operational Health | Phase A - Preserve & harden | P0 | Implementation | Health | Split liveness/readiness semantics: process live, DB ready, optional dependency status. | M01 |  | ☐
M03 | Structured Logging, Error Contracts & Operational Health | Phase A - Preserve & harden | P0 | Implementation | Metrics | At minimum record counts/latency for auth failures, assignment conflicts, timesheet reviews, billing triggers and invoice transitions. | M01 |  | ☐
M03 | Structured Logging, Error Contracts & Operational Health | Phase A - Preserve & harden | P0 | Implementation | Tests | Assert no stack traces/secrets reach production responses and request IDs appear consistently. | M01 |  | ☐
M03 | Structured Logging, Error Contracts & Operational Health | Phase A - Preserve & harden | P0 | Acceptance | Acceptance Criteria | A production error can be traced by request ID. | M01 |  | ☐
M03 | Structured Logging, Error Contracts & Operational Health | Phase A - Preserve & harden | P0 | Acceptance | Acceptance Criteria | Client responses use stable domain error codes. | M01 |  | ☐
M03 | Structured Logging, Error Contracts & Operational Health | Phase A - Preserve & harden | P0 | Acceptance | Acceptance Criteria | Logs contain no raw passwords/JWTs/document contents. | M01 |  | ☐
M04 | Transactional Audit Logging Foundation | Phase A - Preserve & harden | P0 | Implementation | Database | Add `audit_log(id, actor_user_id, actor_role, action, entity_type, entity_id, before_json, after_json, request_id, created_at)` with indexes on entity and actor/time. | M01,M03 |  | ☐
M04 | Transactional Audit Logging Foundation | Phase A - Preserve & harden | P0 | Implementation | Backend | Add `auditRepository`/`auditService`; writes must accept the caller transaction connection so the business mutation and audit record commit/rollback together. | M01,M03 |  | ☐
M04 | Transactional Audit Logging Foundation | Phase A - Preserve & harden | P0 | Implementation | Coverage | Instrument assignment create/release/allocation, project/requirement changes, timesheet submit/edit/review, document verification, candidate decisions, rate changes, milestone changes, invoice transitions and payment records as those modules ship. | M01,M03 |  | ☐
M04 | Transactional Audit Logging Foundation | Phase A - Preserve & harden | P0 | Implementation | Security | Redact secrets and large binary/document content; audit references metadata/IDs only. | M01,M03 |  | ☐
M04 | Transactional Audit Logging Foundation | Phase A - Preserve & harden | P0 | Implementation | Frontend | Add an entity-level timeline drawer later for authorized Vendor/PM users; do not expose cross-tenant audit entries. | M01,M03 |  | ☐
M04 | Transactional Audit Logging Foundation | Phase A - Preserve & harden | P0 | Implementation | Tests | Prove rollback removes the audit row, successful mutation creates exactly one audit record, and before/after payloads match the committed state. | M01,M03 |  | ☐
M04 | Transactional Audit Logging Foundation | Phase A - Preserve & harden | P0 | Acceptance | Acceptance Criteria | Every critical mutation has an audit record with actor and timestamp. | M01,M03 |  | ☐
M04 | Transactional Audit Logging Foundation | Phase A - Preserve & harden | P0 | Acceptance | Acceptance Criteria | Audit writes are transactionally consistent with the business change. | M01,M03 |  | ☐
M04 | Transactional Audit Logging Foundation | Phase A - Preserve & harden | P0 | Acceptance | Acceptance Criteria | Cross-tenant users cannot query another tenant/project audit history. | M01,M03 |  | ☐
M05 | API Scalability, Search/Filtering & API Documentation | Phase A - Preserve & harden | P0 | Implementation | API | Adopt consistent query parameters: `page`, `pageSize`, `sort`, `order`, plus domain filters. Return `{items,page,page_size,total,total_pages}`. | M01,M03 |  | ☐
M05 | API Scalability, Search/Filtering & API Documentation | Phase A - Preserve & harden | P0 | Implementation | Database | Add/verify composite indexes supporting vendor+status/skill, project+status/date, timesheet+project/status/date, invoice+vendor/status/date and candidate pipeline later. | M01,M03 |  | ☐
M05 | API Scalability, Search/Filtering & API Documentation | Phase A - Preserve & harden | P0 | Implementation | Search | Contractors: name/email/skill/status; projects: name/client/status/date; timesheets: project/contractor/status/date; invoices: project/status/date/number when introduced. | M01,M03 |  | ☐
M05 | API Scalability, Search/Filtering & API Documentation | Phase A - Preserve & harden | P0 | Implementation | Backend | Move filtering/pagination into repository SQL; never fetch-all then filter in JavaScript. | M01,M03 |  | ☐
M05 | API Scalability, Search/Filtering & API Documentation | Phase A - Preserve & harden | P0 | Implementation | Frontend | Reusable table/list filter bar, debounced text search, URL-synced filters, empty/loading/error states and pagination controls. | M01,M03 |  | ☐
M05 | API Scalability, Search/Filtering & API Documentation | Phase A - Preserve & harden | P0 | Implementation | Docs | Add OpenAPI specification and generated/checked API examples for every route; document auth requirements and error codes. | M01,M03 |  | ☐
M05 | API Scalability, Search/Filtering & API Documentation | Phase A - Preserve & harden | P0 | Implementation | Tests | Verify pagination totals, filter combinations, stable sort, authorization scoping and index-friendly query shapes. | M01,M03 |  | ☐
M05 | API Scalability, Search/Filtering & API Documentation | Phase A - Preserve & harden | P0 | Acceptance | Acceptance Criteria | No main list endpoint is unbounded. | M01,M03 |  | ☐
M05 | API Scalability, Search/Filtering & API Documentation | Phase A - Preserve & harden | P0 | Acceptance | Acceptance Criteria | Filters remain tenant-scoped in SQL. | M01,M03 |  | ☐
M05 | API Scalability, Search/Filtering & API Documentation | Phase A - Preserve & harden | P0 | Acceptance | Acceptance Criteria | API documentation matches implemented routes and payloads. | M01,M03 |  | ☐
M06 | Timesheet Workflow Completion | Phase B - Workforce operations | P1 | Implementation | Database | Add `description`, `rejection_reason`, explicit `submitted_at`; migrate status enum to `DRAFT,SUBMITTED,APPROVED,REJECTED` and map existing PENDING -> SUBMITTED. | M01,M04,M05 |  | ☐
M06 | Timesheet Workflow Completion | Phase B - Workforce operations | P1 | Implementation | Contractor API | Allow save/edit DRAFT entries; add submit-week/submit-selected action that atomically transitions owned DRAFT/REJECTED rows to SUBMITTED after validation. | M01,M04,M05 |  | ☐
M06 | Timesheet Workflow Completion | Phase B - Workforce operations | P1 | Implementation | PM API | List SUBMITTED rows; require non-blank rejection reason for REJECTED; add bulk approve/reject for selected entries with deterministic lock ordering by timesheet id. | M01,M04,M05 |  | ☐
M06 | Timesheet Workflow Completion | Phase B - Workforce operations | P1 | Implementation | Business rules | Keep project/date/allocation validation server-side; APPROVED rows immutable; rejected rows editable by owner; resubmission clears prior review fields while preserving audit history. | M01,M04,M05 |  | ☐
M06 | Timesheet Workflow Completion | Phase B - Workforce operations | P1 | Implementation | Policies | Retain current 24h/day ceiling initially; add hooks for project-specific daily/weekly/weekend/backdate policies in M10 rather than hard-coding a universal 40h week. | M01,M04,M05 |  | ☐
M06 | Timesheet Workflow Completion | Phase B - Workforce operations | P1 | Implementation | Frontend | Weekly timesheet workspace: day rows, descriptions, draft state, submit-week action, rejection reason banner, edit/resubmit path, PM bulk review table. | M01,M04,M05 |  | ☐
M06 | Timesheet Workflow Completion | Phase B - Workforce operations | P1 | Implementation | Billing integration | Milestone evaluation runs only after APPROVED transitions; draft/submitted/rejected hours never become billable. | M01,M04,M05 |  | ☐
M06 | Timesheet Workflow Completion | Phase B - Workforce operations | P1 | Implementation | Tests | State-transition matrix, rejection reason required, weekly submit ownership, duplicate date, allocation capacity with DRAFT/SUBMITTED reservations, bulk review race safety, resubmission audit. | M01,M04,M05 |  | ☐
M06 | Timesheet Workflow Completion | Phase B - Workforce operations | P1 | Acceptance | Acceptance Criteria | Contractor can save a week as draft and explicitly submit it. | M01,M04,M05 |  | ☐
M06 | Timesheet Workflow Completion | Phase B - Workforce operations | P1 | Acceptance | Acceptance Criteria | PM rejection always explains why. | M01,M04,M05 |  | ☐
M06 | Timesheet Workflow Completion | Phase B - Workforce operations | P1 | Acceptance | Acceptance Criteria | Contractor can correct and resubmit only rejected work. | M01,M04,M05 |  | ☐
M06 | Timesheet Workflow Completion | Phase B - Workforce operations | P1 | Acceptance | Acceptance Criteria | Only approved hours affect milestone/billing. | M01,M04,M05 |  | ☐
M07 | Contractor Profile & Multi-Skill Model | Phase B - Workforce operations | P1 | Implementation | Database | Add `skills` catalog and `contractor_skills(contractor_id, skill_id, proficiency, years_experience, is_primary)`; backfill current FRONTEND/BACKEND/QA/DEVOPS/DATA values. | M01,M05 |  | ☐
M07 | Contractor Profile & Multi-Skill Model | Phase B - Workforce operations | P1 | Implementation | Migration | Add `skill_id` to project requirements, backfill from existing enum, update queries, then drop/retire enum columns only after parity tests. | M01,M05 |  | ☐
M07 | Contractor Profile & Multi-Skill Model | Phase B - Workforce operations | P1 | Implementation | Profile | Add phone, headline/role, total experience years and optional notes; keep only business-relevant fields. | M01,M05 |  | ☐
M07 | Contractor Profile & Multi-Skill Model | Phase B - Workforce operations | P1 | Implementation | Backend | Repositories/services for skill catalog and contractor skill CRUD; vendor can manage profile fields, contractor can maintain allowed self-service fields based on a documented ownership matrix. | M01,M05 |  | ☐
M07 | Contractor Profile & Multi-Skill Model | Phase B - Workforce operations | P1 | Implementation | Matching | Eligible-contractor queries match any verified contractor skill rather than one equality field; primary skill is presentation only. | M01,M05 |  | ☐
M07 | Contractor Profile & Multi-Skill Model | Phase B - Workforce operations | P1 | Implementation | Frontend | Contractor detail/profile with skill chips, proficiency, experience; vendor filters by multiple skills. | M01,M05 |  | ☐
M07 | Contractor Profile & Multi-Skill Model | Phase B - Workforce operations | P1 | Implementation | Tests | Backfill parity, duplicate skill prevention, ownership, skill add/remove effect on future eligibility only. | M01,M05 |  | ☐
M07 | Contractor Profile & Multi-Skill Model | Phase B - Workforce operations | P1 | Acceptance | Acceptance Criteria | A contractor can hold multiple skills with proficiency/experience. | M01,M05 |  | ☐
M07 | Contractor Profile & Multi-Skill Model | Phase B - Workforce operations | P1 | Acceptance | Acceptance Criteria | Existing requirements continue matching after migration. | M01,M05 |  | ☐
M07 | Contractor Profile & Multi-Skill Model | Phase B - Workforce operations | P1 | Acceptance | Acceptance Criteria | Changing skills never rewrites historical assignment/billing records. | M01,M05 |  | ☐
M08 | Contractor Document Verification & Compliance Gate | Phase B - Workforce operations | P1 | Implementation | Database | Add `contractor_documents` with type, storage key/url, status PENDING/VERIFIED/REJECTED/EXPIRED, expiry_date, verified_by, verified_at, rejection_reason, timestamps. | M04,M07 |  | ☐
M08 | Contractor Document Verification & Compliance Gate | Phase B - Workforce operations | P1 | Implementation | Policy | Define a small required-document catalog (e.g. ID, PAN/tax, qualification/experience as configured) and derive overall contractor compliance status from required docs. | M04,M07 |  | ☐
M08 | Contractor Document Verification & Compliance Gate | Phase B - Workforce operations | P1 | Implementation | Storage | Create a storage abstraction; local/dev driver for portfolio use and object-storage compatible interface for production. Persist metadata, not binaries, in MySQL. | M04,M07 |  | ☐
M08 | Contractor Document Verification & Compliance Gate | Phase B - Workforce operations | P1 | Implementation | Security | Validate extension/MIME/content signature, size limits and authorization; use signed/authorized downloads, never public raw paths. | M04,M07 |  | ☐
M08 | Contractor Document Verification & Compliance Gate | Phase B - Workforce operations | P1 | Implementation | Backend | Vendor uploads/manages docs; authorized PM/client may view verification summary but not unrelated vendor private documents. Verification action writes audit record. | M04,M07 |  | ☐
M08 | Contractor Document Verification & Compliance Gate | Phase B - Workforce operations | P1 | Implementation | Eligibility | Assignment/candidate eligibility rejects contractors whose required compliance status is not VERIFIED or whose required document expires before/during assignment dates. | M04,M07 |  | ☐
M08 | Contractor Document Verification & Compliance Gate | Phase B - Workforce operations | P1 | Implementation | Frontend | Compliance checklist, upload status, rejection reason, expiry warnings, verification queue. | M04,M07 |  | ☐
M08 | Contractor Document Verification & Compliance Gate | Phase B - Workforce operations | P1 | Implementation | Tests | Unauthorized file access, invalid files, status transitions, expiry gating and assignment rejection until verified. | M04,M07 |  | ☐
M08 | Contractor Document Verification & Compliance Gate | Phase B - Workforce operations | P1 | Acceptance | Acceptance Criteria | Unverified contractor cannot be assigned/accepted. | M04,M07 |  | ☐
M08 | Contractor Document Verification & Compliance Gate | Phase B - Workforce operations | P1 | Acceptance | Acceptance Criteria | Verification decision is auditable and rejection reason is visible. | M04,M07 |  | ☐
M08 | Contractor Document Verification & Compliance Gate | Phase B - Workforce operations | P1 | Acceptance | Acceptance Criteria | Expired mandatory documents remove future eligibility without deleting history. | M04,M07 |  | ☐
M09 | Client Management, Vendor-Client Relationships & Project Visibility | Phase B - Workforce operations | P1 | Implementation | Database | Add `client_vendor_relationships(client_company_id,vendor_id,status,invited_by,accepted_at,...)` and `project_vendors(project_id,vendor_id,status,...)` for project-level sourcing access. | M02,M04,M05 |  | ☐
M09 | Client Management, Vendor-Client Relationships & Project Visibility | Phase B - Workforce operations | P1 | Implementation | Onboarding | Stop unrestricted company-name claiming: new PM membership should require an invitation/verified company membership flow once a company exists; preserve a controlled first-company bootstrap path for demo/admin setup. | M02,M04,M05 |  | ☐
M09 | Client Management, Vendor-Client Relationships & Project Visibility | Phase B - Workforce operations | P1 | Implementation | PM flow | PM can invite/select connected vendor(s) for a project; revoke future sourcing without deleting historical assignments. | M02,M04,M05 |  | ☐
M09 | Client Management, Vendor-Client Relationships & Project Visibility | Phase B - Workforce operations | P1 | Implementation | Vendor flow | Vendor Clients page shows connected companies, PM contacts, active projects, open requirements, deployed contractors and invoice/payment summary once available. | M02,M04,M05 |  | ☐
M09 | Client Management, Vendor-Client Relationships & Project Visibility | Phase B - Workforce operations | P1 | Implementation | Authorization | Vendor `/projects`, requirement and candidate queries must join through active `project_vendors`; unauthorized project IDs return the same 404 pattern used elsewhere. | M02,M04,M05 |  | ☐
M09 | Client Management, Vendor-Client Relationships & Project Visibility | Phase B - Workforce operations | P1 | Implementation | Frontend | Client directory/detail pages for Vendor; vendor access management within PM project view. | M02,M04,M05 |  | ☐
M09 | Client Management, Vendor-Client Relationships & Project Visibility | Phase B - Workforce operations | P1 | Implementation | Tests | Two vendors/two clients matrix proving no cross-project visibility or staffing outside an active relationship. | M02,M04,M05 |  | ☐
M09 | Client Management, Vendor-Client Relationships & Project Visibility | Phase B - Workforce operations | P1 | Acceptance | Acceptance Criteria | Vendor sees only authorized client/project demand. | M02,M04,M05 |  | ☐
M09 | Client Management, Vendor-Client Relationships & Project Visibility | Phase B - Workforce operations | P1 | Acceptance | Acceptance Criteria | PM can connect/remove a vendor from future sourcing. | M02,M04,M05 |  | ☐
M09 | Client Management, Vendor-Client Relationships & Project Visibility | Phase B - Workforce operations | P1 | Acceptance | Acceptance Criteria | Vendor has a real client-management view without turning the project into a generic CRM. | M02,M04,M05 |  | ☐
M10 | Project, Requirement, Budget & Time-Policy Lifecycle | Phase B - Workforce operations | P1 | Implementation | Database | Add `budget DECIMAL`, `currency CHAR(3)`, optional `max_hours_per_day`, `max_hours_per_week`, `allow_weekend`, `backdate_limit_days`; add requirement `status OPEN/CLOSED` and optional description. | M04,M09 |  | ☐
M10 | Project, Requirement, Budget & Time-Policy Lifecycle | Phase B - Workforce operations | P1 | Implementation | Project API | Add controlled PATCH for name/description/dates/budget/expected_hours/time policies/status; validate against committed data. | M04,M09 |  | ☐
M10 | Project, Requirement, Budget & Time-Policy Lifecycle | Phase B - Workforce operations | P1 | Implementation | Safety | Cannot reduce expected_hours below allocated or approved hours; cannot move dates so existing assignments/timesheets fall outside; cannot complete while there are submitted timesheets or unresolved billing eligibility without an explicit resolution path. | M04,M09 |  | ☐
M10 | Project, Requirement, Budget & Time-Policy Lifecycle | Phase B - Workforce operations | P1 | Implementation | Requirement API | Increase/decrease required_count, close/reopen requirement. Required count cannot drop below already accepted/assigned contractors; do not delete historical requirements. | M04,M09 |  | ☐
M10 | Project, Requirement, Budget & Time-Policy Lifecycle | Phase B - Workforce operations | P1 | Implementation | Status | Define explicit transitions ACTIVE <-> ON_HOLD, ACTIVE/ON_HOLD -> COMPLETED, ACTIVE/ON_HOLD -> CANCELLED (new), with side effects documented. | M04,M09 |  | ☐
M10 | Project, Requirement, Budget & Time-Policy Lifecycle | Phase B - Workforce operations | P1 | Implementation | Timesheet integration | M06 validation reads project-specific policy values; ON_HOLD/CANCELLED/COMPLETED block new submissions. | M04,M09 |  | ☐
M10 | Project, Requirement, Budget & Time-Policy Lifecycle | Phase B - Workforce operations | P1 | Implementation | Frontend | Project settings/edit drawer, requirement editor, budget + policy cards, clear blocked-edit reasons. | M04,M09 |  | ☐
M10 | Project, Requirement, Budget & Time-Policy Lifecycle | Phase B - Workforce operations | P1 | Implementation | Tests | Every invalid date/hours/budget transition, requirement decrease, status transition and existing-data safeguard. | M04,M09 |  | ☐
M10 | Project, Requirement, Budget & Time-Policy Lifecycle | Phase B - Workforce operations | P1 | Acceptance | Acceptance Criteria | Project can be edited without corrupting assignments/timesheets. | M04,M09 |  | ☐
M10 | Project, Requirement, Budget & Time-Policy Lifecycle | Phase B - Workforce operations | P1 | Acceptance | Acceptance Criteria | Budget and currency exist and are available to reporting. | M04,M09 |  | ☐
M10 | Project, Requirement, Budget & Time-Policy Lifecycle | Phase B - Workforce operations | P1 | Acceptance | Acceptance Criteria | Requirements can be managed after creation with safe lower bounds. | M04,M09 |  | ☐
M11 | Contractor Availability & Date-Based Assignment Lifecycle | Phase B - Workforce operations | P1 | Implementation | Database | Add assignment `start_date,end_date,actual_end_date,release_reason,rate_card_id/rate snapshot later`; add `contractor_unavailability(contractor_id,start_date,end_date,reason,status)`. | M07,M08,M10 |  | ☐
M11 | Contractor Availability & Date-Based Assignment Lifecycle | Phase B - Workforce operations | P1 | Implementation | Migration | Remove the generated one-active-assignment uniqueness only after a transactionally safe overlap query/locking strategy and tests exist. | M07,M08,M10 |  | ☐
M11 | Contractor Availability & Date-Based Assignment Lifecycle | Phase B - Workforce operations | P1 | Implementation | Conflict rule | Before candidate acceptance/assignment, reject any date overlap with another non-released assignment; lock contractor + relevant assignment range inside the transaction. | M07,M08,M10 |  | ☐
M11 | Contractor Availability & Date-Based Assignment Lifecycle | Phase B - Workforce operations | P1 | Implementation | Availability | Vendor/contractor can record planned unavailable ranges; eligibility rejects overlapping unavailability. | M07,M08,M10 |  | ☐
M11 | Contractor Availability & Date-Based Assignment Lifecycle | Phase B - Workforce operations | P1 | Implementation | Release | Add authorized individual release with actual last working date and reason; historical assignment stays intact. Release frees future eligibility. | M07,M08,M10 |  | ☐
M11 | Contractor Availability & Date-Based Assignment Lifecycle | Phase B - Workforce operations | P1 | Implementation | PM allocation | Allocated hours remain project-specific; validate allocation against assignment dates and project capacity. | M07,M08,M10 |  | ☐
M11 | Contractor Availability & Date-Based Assignment Lifecycle | Phase B - Workforce operations | P1 | Implementation | Frontend | Availability calendar/list, assignment dates, release action, conflict explanation and upcoming assignment display. | M07,M08,M10 |  | ☐
M11 | Contractor Availability & Date-Based Assignment Lifecycle | Phase B - Workforce operations | P1 | Implementation | Tests | Boundary dates (touching vs overlapping), concurrent acceptance, release/reassign, unavailability conflicts, project completion releasing remaining active assignments. | M07,M08,M10 |  | ☐
M11 | Contractor Availability & Date-Based Assignment Lifecycle | Phase B - Workforce operations | P1 | Acceptance | Acceptance Criteria | Contractor can hold sequential future assignments without overlap. | M07,M08,M10 |  | ☐
M11 | Contractor Availability & Date-Based Assignment Lifecycle | Phase B - Workforce operations | P1 | Acceptance | Acceptance Criteria | Overlapping assignments are rejected race-safely. | M07,M08,M10 |  | ☐
M11 | Contractor Availability & Date-Based Assignment Lifecycle | Phase B - Workforce operations | P1 | Acceptance | Acceptance Criteria | One contractor can be released without completing the project. | M07,M08,M10 |  | ☐
M12 | Candidate Submission -> PM Acceptance Workflow | Phase B - Workforce operations | P1 | Implementation | Database | Add `candidate_submissions` with project, requirement, contractor, vendor, proposed dates/rate, status SUBMITTED/SHORTLISTED/ACCEPTED/REJECTED/WITHDRAWN, vendor_note, pm_note, timestamps/reviewer. | M09,M11 |  | ☐
M12 | Candidate Submission -> PM Acceptance Workflow | Phase B - Workforce operations | P1 | Implementation | Vendor API | Submit eligible contractor to an authorized requirement; withdraw only before acceptance; prevent duplicate active submission for same contractor+requirement. | M09,M11 |  | ☐
M12 | Candidate Submission -> PM Acceptance Workflow | Phase B - Workforce operations | P1 | Implementation | PM API | Review candidate, shortlist, accept or reject with reason. Acceptance runs in one transaction and rechecks project/vendor access, open requirement capacity, compliance, skill, date availability and conflicts. | M09,M11 |  | ☐
M12 | Candidate Submission -> PM Acceptance Workflow | Phase B - Workforce operations | P1 | Implementation | Assignment | Only ACCEPTED candidate creates the project_assignment row; retire direct vendor assignment from normal UI after migration. | M09,M11 |  | ☐
M12 | Candidate Submission -> PM Acceptance Workflow | Phase B - Workforce operations | P1 | Implementation | Rate | Snapshot proposed/selected assignment rate or rate-card reference at acceptance once M15 is available; until then preserve current hourly_rate behavior with explicit migration note. | M09,M11 |  | ☐
M12 | Candidate Submission -> PM Acceptance Workflow | Phase B - Workforce operations | P1 | Implementation | Frontend | Vendor requirement candidate picker + submission status; PM candidate queue/detail + accept/reject; contractor sees assignment only after acceptance. | M09,M11 |  | ☐
M12 | Candidate Submission -> PM Acceptance Workflow | Phase B - Workforce operations | P1 | Implementation | Audit | Every submission/status transition is logged. | M09,M11 |  | ☐
M12 | Candidate Submission -> PM Acceptance Workflow | Phase B - Workforce operations | P1 | Implementation | Tests | Double-submit, two PM acceptance races on last slot, compliance expiry between submit/accept, vendor-project access revocation, withdrawal and rejection. | M09,M11 |  | ☐
M12 | Candidate Submission -> PM Acceptance Workflow | Phase B - Workforce operations | P1 | Acceptance | Acceptance Criteria | Vendor cannot directly place a worker into a client project. | M09,M11 |  | ☐
M12 | Candidate Submission -> PM Acceptance Workflow | Phase B - Workforce operations | P1 | Acceptance | Acceptance Criteria | PM acceptance is the only normal path that creates an assignment. | M09,M11 |  | ☐
M12 | Candidate Submission -> PM Acceptance Workflow | Phase B - Workforce operations | P1 | Acceptance | Acceptance Criteria | Last-slot and overlap races cannot over-assign. | M09,M11 |  | ☐
M13 | Staffing Pipeline, Approval SLA & Escalation | Phase B - Workforce operations | P1 | Implementation | Derived metrics | For each requirement derive available/submitted/shortlisted/accepted/assigned/open counts; do not store counts that can drift. | M12,M10 |  | ☐
M13 | Staffing Pipeline, Approval SLA & Escalation | Phase B - Workforce operations | P1 | Implementation | SLA policy | Add project/client setting for candidate_response_sla_hours and later reuse a generic approval SLA model for timesheets/invoices. | M12,M10 |  | ☐
M13 | Staffing Pipeline, Approval SLA & Escalation | Phase B - Workforce operations | P1 | Implementation | Status | Compute `due_at`/breach at read time from submitted_at + policy; optionally persist escalation acknowledgement, not the derived breach itself. | M12,M10 |  | ☐
M13 | Staffing Pipeline, Approval SLA & Escalation | Phase B - Workforce operations | P1 | Implementation | Dashboard | Vendor sees requirements with stalled submissions; PM sees oldest candidate reviews and open demand. | M12,M10 |  | ☐
M13 | Staffing Pipeline, Approval SLA & Escalation | Phase B - Workforce operations | P1 | Implementation | Filters | By client/project/skill/status/SLA breached. | M12,M10 |  | ☐
M13 | Staffing Pipeline, Approval SLA & Escalation | Phase B - Workforce operations | P1 | Implementation | Tests | Correct funnel counts under rejection/withdrawal/acceptance, SLA timezone boundaries and access scoping. | M12,M10 |  | ☐
M13 | Staffing Pipeline, Approval SLA & Escalation | Phase B - Workforce operations | P1 | Acceptance | Acceptance Criteria | One screen answers how many positions are still open and where candidates are stuck. | M12,M10 |  | ☐
M13 | Staffing Pipeline, Approval SLA & Escalation | Phase B - Workforce operations | P1 | Acceptance | Acceptance Criteria | SLA breach is based on explicit policy/time, not a fabricated status. | M12,M10 |  | ☐
M14 | In-App Notifications & Preferences | Phase B - Workforce operations | P1 | Implementation | Database | Add `notifications` and `notification_preferences` (event type, in-app enabled, email later, quiet hours optional later). | M06,M12,M13 |  | ☐
M14 | In-App Notifications & Preferences | Phase B - Workforce operations | P1 | Implementation | Backend | Create notification service called only after business commit; notification failure must never roll back staffing/timesheet/invoice state. | M06,M12,M13 |  | ☐
M14 | In-App Notifications & Preferences | Phase B - Workforce operations | P1 | Implementation | Events | Start with candidate submitted/accepted/rejected, assignment created/released, timesheet submitted/approved/rejected, document expiring, milestone met/billing eligible. Extend invoice/payment events in M17-M19. | M06,M12,M13 |  | ☐
M14 | In-App Notifications & Preferences | Phase B - Workforce operations | P1 | Implementation | Frontend | Bell/inbox, unread count, mark read/all read, deep links to relevant entity, per-event preference page. | M06,M12,M13 |  | ☐
M14 | In-App Notifications & Preferences | Phase B - Workforce operations | P1 | Implementation | Privacy | Keep messages generic enough for shared screens; do not include sensitive document content. | M06,M12,M13 |  | ☐
M14 | In-App Notifications & Preferences | Phase B - Workforce operations | P1 | Implementation | Reliability | For portfolio scale, persisted in-app notification rows are sufficient; add an outbox/worker only if deployment reliability later requires it. | M06,M12,M13 |  | ☐
M14 | In-App Notifications & Preferences | Phase B - Workforce operations | P1 | Implementation | Tests | No duplicate notification on retry/idempotent mutation, correct recipient role, deep-link authorization. | M06,M12,M13 |  | ☐
M14 | In-App Notifications & Preferences | Phase B - Workforce operations | P1 | Acceptance | Acceptance Criteria | A user can see actionable state changes without manually polling every page. | M06,M12,M13 |  | ☐
M14 | In-App Notifications & Preferences | Phase B - Workforce operations | P1 | Acceptance | Acceptance Criteria | Notification failure cannot undo a committed business transaction. | M06,M12,M13 |  | ☐
M14 | In-App Notifications & Preferences | Phase B - Workforce operations | P1 | Acceptance | Acceptance Criteria | Users can disable non-critical event types. | M06,M12,M13 |  | ☐
M15 | Rate Cards, Assignment Rate Snapshots & Rate History | Phase C - Commercial lifecycle | P1 | Implementation | Database | Add `rate_cards(client_company_id,vendor_id,skill_id,effective_from,effective_to,bill_rate,cost_rate,currency,status)`; add assignment `bill_rate_snapshot,cost_rate_snapshot,currency,rate_card_id`. | M09,M11 |  | ☐
M15 | Rate Cards, Assignment Rate Snapshots & Rate History | Phase C - Commercial lifecycle | P1 | Implementation | Compatibility | Keep contractors.hourly_rate as a legacy/default rate initially; do not rewrite historical milestone_billings. | M09,M11 |  | ☐
M15 | Rate Cards, Assignment Rate Snapshots & Rate History | Phase C - Commercial lifecycle | P1 | Implementation | Resolution | At candidate acceptance/assignment, resolve an active rate card (or explicit approved override) and snapshot rates onto the assignment. | M09,M11 |  | ☐
M15 | Rate Cards, Assignment Rate Snapshots & Rate History | Phase C - Commercial lifecycle | P1 | Implementation | Rules | Rate changes affect future/new assignments or explicit future effective periods only; approved historical work always uses the assignment/billing snapshot. | M09,M11 |  | ☐
M15 | Rate Cards, Assignment Rate Snapshots & Rate History | Phase C - Commercial lifecycle | P1 | Implementation | Backend | Rate-card CRUD scoped to vendor+client relationship, effective-date overlap validation, audit every rate change. | M09,M11 |  | ☐
M15 | Rate Cards, Assignment Rate Snapshots & Rate History | Phase C - Commercial lifecycle | P1 | Implementation | Frontend | Vendor rate-card page by client/skill, effective dates, current/upcoming rates; PM can view agreed bill rate where authorized. | M09,M11 |  | ☐
M15 | Rate Cards, Assignment Rate Snapshots & Rate History | Phase C - Commercial lifecycle | P1 | Implementation | Tests | Effective-date boundary, overlapping rate-card rejection, historical snapshot immutability, currency consistency. | M09,M11 |  | ☐
M15 | Rate Cards, Assignment Rate Snapshots & Rate History | Phase C - Commercial lifecycle | P1 | Acceptance | Acceptance Criteria | Same skill can have different rates for different clients/projects. | M09,M11 |  | ☐
M15 | Rate Cards, Assignment Rate Snapshots & Rate History | Phase C - Commercial lifecycle | P1 | Acceptance | Acceptance Criteria | Historical billing never changes when a rate card changes. | M09,M11 |  | ☐
M15 | Rate Cards, Assignment Rate Snapshots & Rate History | Phase C - Commercial lifecycle | P1 | Acceptance | Acceptance Criteria | Both bill rate and cost rate are available for later margin analytics. | M09,M11 |  | ☐
M16 | Milestone Management Enhancement | Phase C - Commercial lifecycle | P1 | Implementation | Database | Add milestone description, sequence/order, due_date and optional status metadata needed for display; retain threshold_hours as the trigger source. | M06,M10,M15 |  | ☐
M16 | Milestone Management Enhancement | Phase C - Commercial lifecycle | P1 | Implementation | Lifecycle | Keep threshold evaluation deterministic from approved project hours. Expose PENDING/MET and derive billing/invoicing completeness from contribution records rather than duplicating financial truth. | M06,M10,M15 |  | ☐
M16 | Milestone Management Enhancement | Phase C - Commercial lifecycle | P1 | Implementation | Editing | Allow metadata edits while PENDING; threshold can only change if it does not invalidate already met/approved history. MET milestones become immutable except descriptive notes. | M06,M10,M15 |  | ☐
M16 | Milestone Management Enhancement | Phase C - Commercial lifecycle | P1 | Implementation | Frontend | Project milestone timeline with approved-hours progress, due date, contribution breakdown and billing eligibility state. | M06,M10,M15 |  | ☐
M16 | Milestone Management Enhancement | Phase C - Commercial lifecycle | P1 | Implementation | Billing | Continue creating per-contractor milestone_billings exactly once; use assignment rate snapshots from M15 for new billings. | M06,M10,M15 |  | ☐
M16 | Milestone Management Enhancement | Phase C - Commercial lifecycle | P1 | Implementation | Tests | Threshold edits, already-met immutability, multiple contractors, repeated evaluation idempotency, late-created milestone already below approved hours. | M06,M10,M15 |  | ☐
M16 | Milestone Management Enhancement | Phase C - Commercial lifecycle | P1 | Acceptance | Acceptance Criteria | Milestones are understandable business checkpoints without weakening the current idempotent billing ledger. | M06,M10,M15 |  | ☐
M16 | Milestone Management Enhancement | Phase C - Commercial lifecycle | P1 | Acceptance | Acceptance Criteria | Changing contractor/rate data later cannot alter a met milestone contribution. | M06,M10,M15 |  | ☐
M17 | Invoice Lifecycle Redesign: Billing Queue -> Vendor Draft -> Client Approval | Phase C - Commercial lifecycle | P1 | Implementation | Billing queue | Stop auto-generating invoices from milestoneService. Milestone billings become an “eligible to invoice” queue. | M09,M15,M16,M01 |  | ☐
M17 | Invoice Lifecycle Redesign: Billing Queue -> Vendor Draft -> Client Approval | Phase C - Commercial lifecycle | P1 | Implementation | Database | Normalize invoice header + invoice items. Each item references one milestone_billing_id with UNIQUE constraint so a billing contribution can never be invoiced twice. | M09,M15,M16,M01 |  | ☐
M17 | Invoice Lifecycle Redesign: Billing Queue -> Vendor Draft -> Client Approval | Phase C - Commercial lifecycle | P1 | Implementation | Grouping | A draft invoice may group only compatible eligible billings (same vendor, client company, project, currency; define milestone/billing-period rule explicitly). | M09,M15,M16,M01 |  | ☐
M17 | Invoice Lifecycle Redesign: Billing Queue -> Vendor Draft -> Client Approval | Phase C - Commercial lifecycle | P1 | Implementation | Lifecycle | Use `DRAFT -> SUBMITTED -> APPROVED ¦ REJECTED ¦ CANCELLED`; keep payment state separate for M19. Rejected invoice can be revised/resubmitted under controlled version/history rules. | M09,M15,M16,M01 |  | ☐
M17 | Invoice Lifecycle Redesign: Billing Queue -> Vendor Draft -> Client Approval | Phase C - Commercial lifecycle | P1 | Implementation | Vendor API | List un-invoiced billings, create draft, add/remove eligible items while DRAFT, submit invoice. Financial values come from immutable billings/rate snapshots, never client-provided totals. | M09,M15,M16,M01 |  | ☐
M17 | Invoice Lifecycle Redesign: Billing Queue -> Vendor Draft -> Client Approval | Phase C - Commercial lifecycle | P1 | Implementation | PM API | List SUBMITTED invoices only for owned client projects; approve or reject with mandatory reason, race-safe row lock + conditional update. | M09,M15,M16,M01 |  | ☐
M17 | Invoice Lifecycle Redesign: Billing Queue -> Vendor Draft -> Client Approval | Phase C - Commercial lifecycle | P1 | Implementation | Migration | Document mapping of current PENDING_REVIEW/APPROVED/AUTO_APPROVED/REJECTED demo rows; preserve old audit fields or migrate them into audit history. Do not pretend old vendor approval was client approval. | M09,M15,M16,M01 |  | ☐
M17 | Invoice Lifecycle Redesign: Billing Queue -> Vendor Draft -> Client Approval | Phase C - Commercial lifecycle | P1 | Implementation | Frontend | Vendor billing queue/draft builder/submission; PM invoice review queue; clear lifecycle badges. | M09,M15,M16,M01 |  | ☐
M17 | Invoice Lifecycle Redesign: Billing Queue -> Vendor Draft -> Client Approval | Phase C - Commercial lifecycle | P1 | Implementation | Notifications/Audit | Hook submission/review events into M14 and M04. | M09,M15,M16,M01 |  | ☐
M17 | Invoice Lifecycle Redesign: Billing Queue -> Vendor Draft -> Client Approval | Phase C - Commercial lifecycle | P1 | Implementation | Tests | Double item claim, incompatible grouping, two client reviewers race, cross-tenant project access, reject/revise/resubmit, invoice totals equal item snapshots. | M09,M15,M16,M01 |  | ☐
M17 | Invoice Lifecycle Redesign: Billing Queue -> Vendor Draft -> Client Approval | Phase C - Commercial lifecycle | P1 | Acceptance | Acceptance Criteria | Milestone billing can exist without an invoice. | M09,M15,M16,M01 |  | ☐
M17 | Invoice Lifecycle Redesign: Billing Queue -> Vendor Draft -> Client Approval | Phase C - Commercial lifecycle | P1 | Acceptance | Acceptance Criteria | Vendor explicitly creates/submits invoice. | M09,M15,M16,M01 |  | ☐
M17 | Invoice Lifecycle Redesign: Billing Queue -> Vendor Draft -> Client Approval | Phase C - Commercial lifecycle | P1 | Acceptance | Acceptance Criteria | Only client-side PM can approve/reject submitted invoice. | M09,M15,M16,M01 |  | ☐
M17 | Invoice Lifecycle Redesign: Billing Queue -> Vendor Draft -> Client Approval | Phase C - Commercial lifecycle | P1 | Acceptance | Acceptance Criteria | One milestone billing contribution can appear on at most one invoice item. | M09,M15,M16,M01 |  | ☐
M18 | Invoice Numbers, Line Items, Tax & PDF Document | Phase C - Commercial lifecycle | P1 | Implementation | Numbering | Add immutable invoice_number generated from a vendor/year sequence under row lock, e.g. `INV-2026-000123`. | M17 |  | ☐
M18 | Invoice Numbers, Line Items, Tax & PDF Document | Phase C - Commercial lifecycle | P1 | Implementation | Line items | Each item shows contractor/role or skill, milestone/billing period, approved hours, bill rate and amount. Values come from milestone billing + assignment snapshot. | M17 |  | ☐
M18 | Invoice Numbers, Line Items, Tax & PDF Document | Phase C - Commercial lifecycle | P1 | Implementation | Tax | Add explicit tax rate/amount and optional adjustment lines; subtotal + tax + adjustments = total. Currency fixed per invoice. | M17 |  | ☐
M18 | Invoice Numbers, Line Items, Tax & PDF Document | Phase C - Commercial lifecycle | P1 | Implementation | Dates | Add invoice_date, submitted_at and due_date/payment_terms fields. | M17 |  | ☐
M18 | Invoice Numbers, Line Items, Tax & PDF Document | Phase C - Commercial lifecycle | P1 | Implementation | PDF | Generate a server-side PDF from stored invoice data, store it via the same storage abstraction, and provide authorized download. Regenerate only while DRAFT; freeze the submitted/approved document version. | M17 |  | ☐
M18 | Invoice Numbers, Line Items, Tax & PDF Document | Phase C - Commercial lifecycle | P1 | Implementation | Frontend | Invoice detail/preview, PDF download, print-friendly view. | M17 |  | ☐
M18 | Invoice Numbers, Line Items, Tax & PDF Document | Phase C - Commercial lifecycle | P1 | Implementation | Tests | Sequential number race, exact decimal math, item totals, tax rounding, immutable document after submission, unauthorized download. | M17 |  | ☐
M18 | Invoice Numbers, Line Items, Tax & PDF Document | Phase C - Commercial lifecycle | P1 | Acceptance | Acceptance Criteria | Every submitted invoice has a human-readable immutable number. | M17 |  | ☐
M18 | Invoice Numbers, Line Items, Tax & PDF Document | Phase C - Commercial lifecycle | P1 | Acceptance | Acceptance Criteria | PDF values exactly match database line items/totals. | M17 |  | ☐
M18 | Invoice Numbers, Line Items, Tax & PDF Document | Phase C - Commercial lifecycle | P1 | Acceptance | Acceptance Criteria | Invoice can be handed to a finance user without explaining internal database IDs. | M17 |  | ☐
M19 | Payment & Outstanding Tracking | Phase C - Commercial lifecycle | P1 | Implementation | Database | Add `payments(invoice_id,amount,paid_at,reference,method,notes,recorded_by,created_at)`; index invoice/date. | M17,M18 |  | ☐
M19 | Payment & Outstanding Tracking | Phase C - Commercial lifecycle | P1 | Implementation | Business rules | Payment can be recorded only against an APPROVED invoice; sum(payments) cannot exceed invoice total unless explicit credit/adjustment functionality is added later. | M17,M18 |  | ☐
M19 | Payment & Outstanding Tracking | Phase C - Commercial lifecycle | P1 | Implementation | Derived status | Compute UNPAID/PARTIALLY_PAID/PAID from payment sum; compute OVERDUE from due_date + outstanding > 0. Keep this separate from invoice approval lifecycle status. | M17,M18 |  | ☐
M19 | Payment & Outstanding Tracking | Phase C - Commercial lifecycle | P1 | Implementation | Backend | Vendor records payment received; PM can view payment status for own projects. Every payment is audited. | M17,M18 |  | ☐
M19 | Payment & Outstanding Tracking | Phase C - Commercial lifecycle | P1 | Implementation | Frontend | Payment history, record-payment modal, outstanding amount, aging buckets and overdue indicators. | M17,M18 |  | ☐
M19 | Payment & Outstanding Tracking | Phase C - Commercial lifecycle | P1 | Implementation | Notifications | Due-soon/overdue notifications can be added through M14 preferences. | M17,M18 |  | ☐
M19 | Payment & Outstanding Tracking | Phase C - Commercial lifecycle | P1 | Implementation | Tests | Partial payments, exact payoff, overpayment rejection, payment rollback/audit and timezone-safe due-date calculation. | M17,M18 |  | ☐
M19 | Payment & Outstanding Tracking | Phase C - Commercial lifecycle | P1 | Acceptance | Acceptance Criteria | Dashboard can distinguish invoiced, approved, paid and outstanding. | M17,M18 |  | ☐
M19 | Payment & Outstanding Tracking | Phase C - Commercial lifecycle | P1 | Acceptance | Acceptance Criteria | Partial payment history is preserved. | M17,M18 |  | ☐
M19 | Payment & Outstanding Tracking | Phase C - Commercial lifecycle | P1 | Acceptance | Acceptance Criteria | Overdue is a deterministic derived fact, not a manually assigned status. | M17,M18 |  | ☐
M20 | Business Dashboards, Financial Health & CSV Exports | Phase C - Commercial lifecycle | P2 | Implementation | Vendor dashboard | Clients/projects, open requirements, candidate funnel/SLA, active/upcoming contractors, compliance expiry, approved hours, billable-uninvoiced, submitted/approved invoices, paid/outstanding/overdue, margin by client/project/skill. | M05,M10,M13,M15,M19 |  | ☐
M20 | Business Dashboards, Financial Health & CSV Exports | Phase C - Commercial lifecycle | P2 | Implementation | PM dashboard | Project staffing funnel, pending candidate/timesheet/invoice reviews, SLA breaches, budget vs approved work vs invoiced vs paid, milestone progress. | M05,M10,M13,M15,M19 |  | ☐
M20 | Business Dashboards, Financial Health & CSV Exports | Phase C - Commercial lifecycle | P2 | Implementation | Contractor dashboard | Active/upcoming assignments, allocation vs approved/submitted hours, rejected items requiring action, compliance expiries; if cost-rate/payable is modeled, show contractor payable facts instead of client invoice revenue. | M05,M10,M13,M15,M19 |  | ☐
M20 | Business Dashboards, Financial Health & CSV Exports | Phase C - Commercial lifecycle | P2 | Implementation | Budget analytics | Budget utilization = approved/billable project cost against project budget; show planned/allocated/actual as distinct values. | M05,M10,M13,M15,M19 |  | ☐
M20 | Business Dashboards, Financial Health & CSV Exports | Phase C - Commercial lifecycle | P2 | Implementation | Filters | Client/project/vendor/skill/status/date filters with server-side aggregation, not client-side full dataset downloads. | M05,M10,M13,M15,M19 |  | ☐
M20 | Business Dashboards, Financial Health & CSV Exports | Phase C - Commercial lifecycle | P2 | Implementation | CSV | Export contractors/assignments, approved timesheets, invoice headers/items, payments and project financial summary. Use the same filters as the screen. | M05,M10,M13,M15,M19 |  | ☐
M20 | Business Dashboards, Financial Health & CSV Exports | Phase C - Commercial lifecycle | P2 | Implementation | Performance | Add targeted aggregation indexes and query limits; inspect plans for the largest dashboard queries. | M05,M10,M13,M15,M19 |  | ☐
M20 | Business Dashboards, Financial Health & CSV Exports | Phase C - Commercial lifecycle | P2 | Implementation | Tests | Metric definitions against known fixture data, terminology consistency, CSV totals matching API/dashboard values. | M05,M10,M13,M15,M19 |  | ☐
M20 | Business Dashboards, Financial Health & CSV Exports | Phase C - Commercial lifecycle | P2 | Acceptance | Acceptance Criteria | No dashboard uses “revenue/paid” interchangeably. | M05,M10,M13,M15,M19 |  | ☐
M20 | Business Dashboards, Financial Health & CSV Exports | Phase C - Commercial lifecycle | P2 | Acceptance | Acceptance Criteria | Budget, billed, approved, paid and outstanding are distinct. | M05,M10,M13,M15,M19 |  | ☐
M20 | Business Dashboards, Financial Health & CSV Exports | Phase C - Commercial lifecycle | P2 | Acceptance | Acceptance Criteria | Finance/operations can export filtered CSV that reconciles to on-screen totals. | M05,M10,M13,M15,M19 |  | ☐
M21 | Contractor Offboarding, History & Project Close Safeguards | Phase D - Portfolio-grade operations | P2 | Implementation | Assignment | Extend release with planned/actual last working date, release reason and actor. | M11,M19,M04 |  | ☐
M21 | Contractor Offboarding, History & Project Close Safeguards | Phase D - Portfolio-grade operations | P2 | Implementation | Checks | Before release/project completion, surface submitted/rejected timesheets, unbilled milestone contributions, draft/submitted invoices and unpaid approved invoices. Decide which are blockers vs warnings explicitly. | M11,M19,M04 |  | ☐
M21 | Contractor Offboarding, History & Project Close Safeguards | Phase D - Portfolio-grade operations | P2 | Implementation | History | Contractor history page: past assignments, client/project, dates, skills/role, approved hours, rate snapshot and billing/payment facts authorized to Vendor. | M11,M19,M04 |  | ☐
M21 | Contractor Offboarding, History & Project Close Safeguards | Phase D - Portfolio-grade operations | P2 | Implementation | Project close | Completion checklist confirms staffing released, approvals handled and billing status understood; project status change remains explicit, never auto-triggered by hours. | M11,M19,M04 |  | ☐
M21 | Contractor Offboarding, History & Project Close Safeguards | Phase D - Portfolio-grade operations | P2 | Implementation | Audit | All close/release actions recorded. | M11,M19,M04 |  | ☐
M21 | Contractor Offboarding, History & Project Close Safeguards | Phase D - Portfolio-grade operations | P2 | Implementation | Tests | Release with pending work, project completion with unresolved records, historical visibility after contractor status INACTIVE. | M11,M19,M04 |  | ☐
M21 | Contractor Offboarding, History & Project Close Safeguards | Phase D - Portfolio-grade operations | P2 | Acceptance | Acceptance Criteria | Individual release and project completion explain unresolved work instead of silently hiding it. | M11,M19,M04 |  | ☐
M21 | Contractor Offboarding, History & Project Close Safeguards | Phase D - Portfolio-grade operations | P2 | Acceptance | Acceptance Criteria | Historical assignment and financial records remain queryable after offboarding. | M11,M19,M04 |  | ☐
M22 | Production Deployment, Backup, Security & Demo Environment | Phase D - Portfolio-grade operations | P2 | Implementation | Containers | Add Dockerfiles and docker-compose for backend/frontend/MySQL in local demo; migration command must run explicitly and idempotently. | M01,M02,M03,M20 |  | ☐
M22 | Production Deployment, Backup, Security & Demo Environment | Phase D - Portfolio-grade operations | P2 | Implementation | Environment | Separate dev/test/prod config, secure secret handling, strict production CORS, cookie/security settings and storage configuration. | M01,M02,M03,M20 |  | ☐
M22 | Production Deployment, Backup, Security & Demo Environment | Phase D - Portfolio-grade operations | P2 | Implementation | Database ops | Document backup/restore, migration rollback strategy where possible, and test a restore into a fresh environment. | M01,M02,M03,M20 |  | ☐
M22 | Production Deployment, Backup, Security & Demo Environment | Phase D - Portfolio-grade operations | P2 | Implementation | Demo data | Seed a deterministic scenario with Vendor, PM/client, contractors, requirements, candidate submissions, approved/rejected timesheets, milestones, invoice and payment states. | M01,M02,M03,M20 |  | ☐
M22 | Production Deployment, Backup, Security & Demo Environment | Phase D - Portfolio-grade operations | P2 | Implementation | E2E | Add Playwright smoke journeys for Vendor -> candidate submit, PM accept, contractor timesheet, PM review, vendor invoice submit, PM approve, payment record. | M01,M02,M03,M20 |  | ☐
M22 | Production Deployment, Backup, Security & Demo Environment | Phase D - Portfolio-grade operations | P2 | Implementation | Performance | Basic load checks on list/search and concurrent approval/assignment hotspots. | M01,M02,M03,M20 |  | ☐
M22 | Production Deployment, Backup, Security & Demo Environment | Phase D - Portfolio-grade operations | P2 | Implementation | Security review | Dependency audit, headers, file upload limits, authorization matrix and secret scan. | M01,M02,M03,M20 |  | ☐
M22 | Production Deployment, Backup, Security & Demo Environment | Phase D - Portfolio-grade operations | P2 | Implementation | Deployment | Host one demo environment or provide one-command local demo; keep provider-specific choices outside core domain code. | M01,M02,M03,M20 |  | ☐
M22 | Production Deployment, Backup, Security & Demo Environment | Phase D - Portfolio-grade operations | P2 | Acceptance | Acceptance Criteria | Clean checkout can start the complete system with documented commands. | M01,M02,M03,M20 |  | ☐
M22 | Production Deployment, Backup, Security & Demo Environment | Phase D - Portfolio-grade operations | P2 | Acceptance | Acceptance Criteria | Backup restore is tested. | M01,M02,M03,M20 |  | ☐
M22 | Production Deployment, Backup, Security & Demo Environment | Phase D - Portfolio-grade operations | P2 | Acceptance | Acceptance Criteria | A reviewer can exercise the main end-to-end lifecycle with seeded accounts/data. | M01,M02,M03,M20 |  | ☐
M23 | Final Architecture Audit, Release & Internship Story | Phase D - Portfolio-grade operations | P2 | Implementation | Audit | Re-review every migration/service/repository/route/frontend workflow against the final architecture and original spec; list deliberate deviations. | M00-M22 |  | ☐
M23 | Final Architecture Audit, Release & Internship Story | Phase D - Portfolio-grade operations | P2 | Implementation | Security | Authorization matrix test across Vendor/Contractor/PM, including all new client/project/candidate/document/invoice/payment resources. | M00-M22 |  | ☐
M23 | Final Architecture Audit, Release & Internship Story | Phase D - Portfolio-grade operations | P2 | Implementation | Data integrity | Reconcile approved hours -> milestone billings -> invoice items -> invoice totals -> payments; add one automated reconciliation test. | M00-M22 |  | ☐
M23 | Final Architecture Audit, Release & Internship Story | Phase D - Portfolio-grade operations | P2 | Implementation | Docs | Final architecture diagram, ERD, business workflow diagram, API docs, deployment instructions and decision log. | M00-M22 |  | ☐
M23 | Final Architecture Audit, Release & Internship Story | Phase D - Portfolio-grade operations | P2 | Implementation | Release | Tag a stable release (e.g. `v2.0-portfolio` or semantic version chosen at that time) and write release notes separating hackathon MVP from independent extensions. | M00-M22 |  | ☐
M23 | Final Architecture Audit, Release & Internship Story | Phase D - Portfolio-grade operations | P2 | Implementation | Demo | Prepare a 5-8 minute role-switch demo and 2-3 deeper engineering stories: concurrency/locking, immutable financial snapshots/idempotency, and a business-workflow redesign such as candidate acceptance or invoice lifecycle. | M00-M22 |  | ☐
M23 | Final Architecture Audit, Release & Internship Story | Phase D - Portfolio-grade operations | P2 | Implementation | Resume/interview | Describe truthfully: initial MVP built in Workday hackathon; independently audited, hardened and extended after the event. | M00-M22 |  | ☐
M23 | Final Architecture Audit, Release & Internship Story | Phase D - Portfolio-grade operations | P2 | Acceptance | Acceptance Criteria | All critical workflows have automated + manual E2E coverage. | M00-M22 |  | ☐
M23 | Final Architecture Audit, Release & Internship Story | Phase D - Portfolio-grade operations | P2 | Acceptance | Acceptance Criteria | Documentation and demo match actual code. | M00-M22 |  | ☐
M23 | Final Architecture Audit, Release & Internship Story | Phase D - Portfolio-grade operations | P2 | Acceptance | Acceptance Criteria | You can explain why each major change exists and what invariant protects it. | M00-M22 |  | ☐

## Dependencies
Module Dependency Map
Module ID | Module | Depends On | Why dependency matters | Ready?
M00 | Freeze Hackathon Baseline & Repository Governance | None | Baseline / no dependency.
M01 | Automated Regression Suite & CI | M00 | Protect later changes before refactoring business logic.
M02 | Authentication, Session & Account Security Hardening | M01 | Security changes should be regression-tested first.
M03 | Structured Logging, Error Contracts & Operational Health | M01 | Operational diagnostics depend on a stable test baseline.
M04 | Transactional Audit Logging Foundation | M01,M03 | Audit should use request/error context and be present before new workflows.
M05 | API Scalability, Search/Filtering & API Documentation | M01,M03 | Pagination/docs need stable errors and tests.
M06 | Timesheet Workflow Completion | M01,M04,M05 | Timesheet changes should be tested and auditable.
M07 | Contractor Profile & Multi-Skill Model | M01,M05 | Skill migration needs tests and paginated/filterable list foundations.
M08 | Contractor Document Verification & Compliance Gate | M04,M07 | Compliance depends on a richer contractor/skill profile and audit trail.
M09 | Client Management, Vendor-Client Relationships & Project Visibility | M02,M04,M05 | Client/project tenancy depends on hardened auth, audit and query scoping.
M10 | Project, Requirement, Budget & Time-Policy Lifecycle | M04,M09 | Project lifecycle builds on explicit client/vendor access.
M11 | Contractor Availability & Date-Based Assignment Lifecycle | M07,M08,M10 | Assignment eligibility depends on skills, compliance and project lifecycle.
M12 | Candidate Submission -> PM Acceptance Workflow | M09,M11 | Candidate acceptance must revalidate authorized project access and date availability.
M13 | Staffing Pipeline, Approval SLA & Escalation | M12,M10 | Pipeline/SLA derives from candidate submissions and project policy.
M14 | In-App Notifications & Preferences | M06,M12,M13 | Notifications hook into completed workflow transitions.
M15 | Rate Cards, Assignment Rate Snapshots & Rate History | M09,M11 | Rate cards depend on client/vendor relationships and assignment dates.
M16 | Milestone Management Enhancement | M06,M10,M15 | Milestone billing needs stable time/project/rate foundations.
M17 | Invoice Lifecycle Redesign: Billing Queue -> Vendor Draft -> Client Approval | M09,M15,M16,M01 | Invoice redesign consumes immutable milestone billings and agreed rates.
M18 | Invoice Numbers, Line Items, Tax & PDF Document | M17 | Business invoice document depends on the final invoice header/items model.
M19 | Payment & Outstanding Tracking | M17,M18 | Payment exists only after approved invoices and due dates.
M20 | Business Dashboards, Financial Health & CSV Exports | M05,M10,M13,M15,M19 | Financial dashboards/export depend on authoritative budget/rates/invoice/payment facts.
M21 | Contractor Offboarding, History & Project Close Safeguards | M11,M19,M04 | Offboarding must account for assignments, audit and unresolved financial records.
M22 | Production Deployment, Backup, Security & Demo Environment | M01,M02,M03,M20 | Deployment comes after core security/observability/reporting are stable.
M23 | Final Architecture Audit, Release & Internship Story | M00-M22 | Final audit/release validates the entire completed roadmap.

## Releases
Suggested Release Milestones
Release | Modules | Meaning | Done
R0 / v1.0-hackathon | M00 | Frozen historical baseline of the two-day submission. | ☑
R1 / v1.1-foundation | M01-M05 | Tests, CI, security, logs, audit foundation, pagination and API docs. | ☐
R2 / v2.0-workforce | M06-M14 | Complete time workflow, multi-skill/compliance, client/vendor scope, project/assignment lifecycle, candidate pipeline, SLA and notifications. | ☐
R3 / v3.0-commercial | M15-M20 | Rate cards, milestone metadata, correct invoice lifecycle, real invoice documents, payment tracking, financial dashboards and exports. | ☐
R4 / v4.0-portfolio | M21-M23 | Offboarding, deployment, recovery, end-to-end validation and internship-ready release. | ☐

## Legend
How to Use This Tracker
Item | Meaning
Checkbox cells | Click the dropdown in Done/Module Done and switch ☐ to ☑ when completed.
Roadmap completion | Calculated automatically from completed Detailed Checklist rows for that module.
P0 | Foundation / safety work that should be completed before major business expansion.
P1 | Core workforce or commercial capability with direct product value.
P2 | Operational/portfolio maturity after the core lifecycle is stable.
Module exit rule | Implement -> manual E2E -> audit -> automated tests -> docs -> commit/push -> next module.
Scope discipline | Do not add AI screening, payroll, HRMS, generic CRM, bank/payment gateway, microservices or Kubernetes in this roadmap.